## FMR Loan Feedback Inbound
Integration # | Integration | Description | Test Scenario | Test Case | Test Steps | Expected Result
TRI0015 | FMR Loan Feedback Inbound | The Fidelity Inbound File should update SAP Infotype 0014 and 0015 - Deduction and Balance | Execute Inbound File using Program: ZTRI0015_US_FMR_LOAN_IN | 1) Check whether the Fidelity Investments (fmr Loan Feedback Inbound) File is a change-only file sent on weekly basis for a partner | 1) Go to Tcode: AL11 | The program should be able to process record for a partner
|  |  |  | 2) Check whether Fidelity inbound file contains Partner Number, SSN number, Header, Plan Type, Transaction Effective Date, Loan Id, Partners pay period deduction amount and goal amount | 2) Go to Tcode: AL11 | Fidelity inbound file should contains Partner Number, SSN number, Header, Plan Type, Transaction Effective Date, Loan Id, Partners pay period deduction amount and goal amount
|  |  |  | 3) Execute the program: ZTRI0015_US_FMR_LOAN_IN to update IT0014 and IT0015 | 3) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | The program should run successfully and update Infotype 0014 and 0015 - Deduction and Balance
|  |  |  | 4) Check whether system is validating that partner in inbound file is from US country or not | 4) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should check if partner is from US country, The program should throw an error for the non US Partner
|  |  |  | 5) Check whether system is validating if Partner is Active/Unapproved LOA/Approved LOA or not | 5) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should validate if partner is Active/Unapproved LOA/Approved
|  |  |  | 6) Check whether system is not processing record if Partner is PreHire or not | 6) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should not process record if partner is Prehire
|  |  |  | 7) Check whether system is not processing record if Partner is non-partner workforce [NPW] or not | 7) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should not process record if partner is non-partner workforce [NPW]
|  |  |  | 8) Check whether system is validating Fidelity Feedback (Loan Deduction) File is delta or not | 8) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should validate the Fidelity Feedback (Loan Deduction) File is delta
|  |  |  | 9) Check whether system is validating the Deduction amount is zero or not | 9) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should validate if partner is Active/Unapproved LOA/Approved or Terminated
|  |  |  | 10) Check whether system is updating IT0014 with IT0041 "U3" date type or not if Deduction amount is zero and partner is Terminated | 10) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with IT0041 "U3" date type
|  |  |  | 11) Check whether system is updating IT0014 with previous cycle End Date or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not | 11) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with Previous Pay Cycle End date
|  |  |  | 12) Check whether system is updating IT0014 with valid wage type or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not | 12) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with valid wage type
|  |  |  | 13) Check whether system is updating IT0015 with valid Balance or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not | 13) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0015 with valid Balance
|  |  |  | 14) Check whether system is updating IT0014 with WT 1610 for General Loan deduction amount or not if Partner is Active or Unapproved LOA | 14) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with WT 1610 for General Loan deduction amount if Partner is Active or Unapproved LOA
|  |  |  | 15) Check whether system is updating IT0015 with WT 1611 for Balance amount or not if Partner is Active or Unapproved LOA | 15) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0015 with WT 1611 for Balance amount if Partner is Active or Unapproved LOA
|  |  |  | 16) Check whether system is updating IT0014 with WT 1630 for General Loan deduction amount or not if Partner is Approved LOA | 16) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with WT 1630 for General Loan deduction amount if Partner is Approved LOA
|  |  |  | 17) Check whether system is updating IT0015 with WT 1631 for Balance amount or not if Partner is Approved LOA | 17) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0015 with WT 1631 for Balance amount if Partner is Approved LOA
|  |  |  | 18) Check whether system is updating IT0014 with WT 1620 for Home Loan deduction amount or not if Partner is Active or Unapproved LOA | 18) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with WT 1620 for Home Loan deduction amount if Partner is Active or Unapproved LOA
|  |  |  | 19) Check whether system is updating IT0015 with WT 1621 for Balance amount or not if Partner is Active or Unapproved LOA | 19) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0015 with WT 1621 for Balance amount if Partner is Active or Unapproved LOA
|  |  |  | 20) Check whether system is updating IT0014 with WT 1640 for Home Loan deduction amount or not if Partner is Approved LOA | 20) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0014 with WT 1640 for Home Loan deduction amount if Partner is Approved LOA
|  |  |  | 21) Check whether system is updating IT0015 with WT 1641 for Balance amount or not if Partner is Approved LOA | 21) Go to Tcode: SA38 -> ZTRI0015_US_FMR_LOAN_IN | System should update IT0015 with WT 1641 for Balance amount if Partner is Approved LOA
|  |  |  | 22) Check whether system is updating TVARVC table with date in Inbound file or not | 22) Go to Tcode: SE16 -> ZPBN_FMR_LOAN_IN | System should update TVARVC table with date in Inbound file or not
|  |  |  | 23) Check what happens when the program is executed for the second time for the same partner on the same date. | 23) Go to Tcode:SA38, PC00_M10_CALC | The program should overwrite the record in IT0014 and IT0015 for the partner
|  |  |  | 24) Check whether the file contains only the detail records and not the header and trailer records | 24) Go to Tcode: AL11 | The File in AL11 Folder should contain only the detail records and not the header and trailer records
|  |  |  | 25) Execute the program in background | 25) Go to Tcode: SA38 | The background job should run successfully and the spool file should be created

## Test Case1
CLIENT | PYJ(100)
TEST CASE# | 1) Check whether the Fidelity Investments (fmr Loan Feedback Inbound) File is a change-only file sent on weekly basis for a partner
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | The program should be able to process record for a partner
ACTUAL RESULT
COMMENTS
TEST STATUS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case2
CLIENT | PYJ(100)
TEST CASE# | 2) Check whether Fidelity inbound file contains Partner Number, SSN number, Header, Plan Type, Transaction Effective Date, Loan Id, Partners pay period deduction amount and goal amount
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | Fidelity inbound file should contains Partner Number, SSN number, Header, Plan Type, Transaction Effective Date, Loan Id, Partners pay period deduction amount and goal amount
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case3
CLIENT | PYJ(100)
TEST CASE# | 3) Execute the program: ZTRI0015_US_FMR_LOAN_IN to update IT0014 and IT0015
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | The program should run successfully and update Infotype 0014 and 0015 - Deduction and Balance
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case4
CLIENT | PYJ(100)
TEST CASE# | 4) Check whether system is validating that partner in inbound file is from US country or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should check if partner is from US country, The program should throw an error for the non US Partner
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case5
CLIENT | PYJ(100)
TEST CASE# | 5) Check whether system is validating if Partner is Active/Unapproved LOA/Approved LOA or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should validate if partner is Active/Unapproved LOA/Approved
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case6
CLIENT | PYJ(100)
TEST CASE# | 6) Check whether system is not processing record if Partner is PreHire or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should not process record if partner is Prehire
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case7
CLIENT | PYJ(100)
TEST CASE# | 7) Check whether system is not processing record if Partner is non-partner workforce [NPW] or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should not process record if partner is non-partner workforce [NPW]
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case8
CLIENT | PYJ(100)
TEST CASE# | 8) Check whether system is validating Fidelity Feedback (Loan Deduction) File is delta or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should validate the Fidelity Feedback (Loan Deduction) File is delta
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case9
CLIENT | PYJ(100)
TEST CASE# | 9) Check whether system is validating the Deduction amount is zero or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should validate if partner is Active/Unapproved LOA/Approved or Terminated
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case10
CLIENT | PYJ(100)
TEST CASE# | 10) Check whether system is updating IT0014 with IT0041 "U3" date type or not if Deduction amount is zero and partner is Terminated
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with IT0041 "U3" date type
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case11
CLIENT | PYJ(100)
TEST CASE# | 11) Check whether system is updating IT0014 with previous cycle End Date or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with Previous Pay Cycle End date
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case12
CLIENT | PYJ(100)
TEST CASE# | 12) Check whether system is updating IT0014 with valid wage type or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with valid wage type
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case13
CLIENT | PYJ(100)
TEST CASE# | 13) Check whether system is updating IT0015 with valid Balance or not if Deduction amount is zero and partner has change in event for Active/Unapproved LOA/Approved LOA or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with valid Balance
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case14
CLIENT | PYJ(100)
TEST CASE# | 14) Check whether system is updating IT0014 with WT 1610 for General Loan deduction amount or not if Partner is Active or Unapproved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with WT 1610 for General Loan deduction amount if Partner is Active or Unapproved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case15
CLIENT | PYJ(100)
TEST CASE# | 15) Check whether system is updating IT0015 with WT 1611 for Balance amount or not if Partner is Active or Unapproved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with WT 1611 for Balance amount if Partner is Active or Unapproved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case16
CLIENT | PYJ(100)
TEST CASE# | 16) Check whether system is updating IT0014 with WT 1630 for General Loan deduction amount or not if Partner is Approved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with WT 1611 for Balance amount if Partner is Active or Unapproved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case17
CLIENT | PYJ(100)
TEST CASE# | 17) Check whether system is updating IT0015 with WT 1631 for Balance amount or not if Partner is Approved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with WT 1631 for Balance amount if Partner is Approved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case18
CLIENT | PYJ(100)
TEST CASE# | 18) Check whether system is updating IT0014 with WT 1620 for Home Loan deduction amount or not if Partner is Active or Unapproved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with WT 1620 for Home Loan deduction amount if Partner is Active or Unapproved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case19
CLIENT | PYJ(100)
TEST CASE# | 19) Check whether system is updating IT0015 with WT 1621 for Balance amount or not if Partner is Active or Unapproved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with WT 1621 for Balance amount if Partner is Active or Unapproved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case20
CLIENT | PYJ(100)
TEST CASE# | 20) Check whether system is updating IT0014 with WT 1640 for Home Loan deduction amount or not if Partner is Approved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0014 with WT 1640 for Home Loan deduction amount if Partner is Approved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case21
CLIENT | PYJ(100)
TEST CASE# | 21) Check whether system is updating IT0015 with WT 1641 for Balance amount or not if Partner is Approved LOA
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update IT0015 with WT 1641 for Balance amount if Partner is Approved LOA
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case22
CLIENT | PYJ(100)
TEST CASE# | 22) Check whether system is updating TVARVC table with date in Inbound file or not
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | System should update TVARVC table with date in Inbound file or not
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case23
CLIENT | PYJ(100)
TEST CASE# | 23) Check what happens when the program is executed for the second time for the same partner on the same date.
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | The program should overwrite the record in IT0014 and IT0015 for the partner
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case24
CLIENT | PYJ(100)
TEST CASE# | 24) Check whether the file contains only the detail records and not the header and trailer records
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | The File in AL11 Folder should contain only the detail records and not the header and trailer records
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated

## Test Case25
CLIENT | PYJ(100)
TEST CASE# | 25) Execute the program in background
TEST PARTNER ID | 10000032
TESTER | VJADHAV
DATE OF TESTING | 2024.06.21
EXPECTED RESULT | The background job should run successfully and the spool file should be created
ACTUAL RESULT
COMMENTS
TEST STATUS | PASS
#Report Selection Screen
#Input File
#Report Output
#IT0000 of Partner (Ineligible LOA)
#IT0014 Updated
#IT0015 Updated